## Sheet1
Gantt chart | [13 empty] | Name: ______________________________
Score: ___/10
Backyard fence project (example)
| day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
design and plan the fence | 2 days | bar: Backyard fence project (example) 1 to Backyard fence project (example) 2
visit lumberyard and order lumber | 1 day | bar: Backyard fence project (example) 3
order gravel delivery | same day | bar: Backyard fence project (example) 3
buy hardware and fasteners | same day | bar: Backyard fence project (example) 3
dig post holes | 6 days | bar: Backyard fence project (example) 4 to Backyard fence project (example) 9
stop because you hate digging postholes | 1 day | bar: Backyard fence project (example) 10
dig more postholes | 3 days | bar: Backyard fence project (example) 11 to Backyard fence project (example) 13
plane lumber | 2 days | bar: Backyard fence project (example) 14 to Backyard fence project (example) 15
install fence posts | 2 days | bar: Backyard fence project (example) 16 to Backyard fence project (example) 17
attach beams | 1 day | bar: Backyard fence project (example) 18
attach fence boards | 1 day | bar: Backyard fence project (example) 19
stain fence | 1 day | bar: Backyard fence project (example) 20
remember hating digging postholes | same day | bar: Backyard fence project (example) 20
Production Tech Box Project Gantt Chart
| day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
get some knowledge | 4 days
design and plan box | 2 days
figure out materials and cost | 1 day
joint and plane lumber to 1/2" | 1 day
layout cuts on lumber | 1 day
cut out pieces | 1 day
cut joinery | 1 day
cut bottom | 1 day
test assembly | 1 day
glue up | 1 day
sanding | 1 day
paint/varnish | 4 days