## Sheet1
Gantt chart | [9 empty] | Name: ______________________________
Score: ___/10
Table Project Gantt Chart - What do I do next?
| day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
2 days | get some knowledge
2 days | design and plan table
1 day | figure out materials and cost
1 day | joint one face + two edges of all lumber
same day | cut all lumber to rough length (add 1")
same day | glue together pieces for table top and shelf
1 day | plane table top to 1 1/4"" thick
same day | plane shelf and skirt to 1/2" thick
1 day | use table saw to cut legs to 1 1/4 x 1 1/4"
same day | cut all pieces to exact length on mitre saw
same day | cut dados for table clips into skirt parts
1 day | cut tapers on legs
same day | cut chamfer on table top
1 day | label matching parts for each corner: 1-2-3-4
same day | create biscuit slots on legs and skirt
same day | cut notches from corners of shelf on bandsaw
same day | drill dowel holes in the shelf with hand drill
same day | use dowel centres to transfer centres to legs
same day | drill dowel holes in the legs with hand drill
1 day | test assembly
same day | glue up
1 day | sanding
5 days | paint/varnish